## Sheet1
Date | Type | Mistake/note | Effect | Corrected in Rev2? | Comment
2016-04-09 | Silkscreen | YQ on silkscreen is backwards for both front and back | Visual | Yes | Done
2016-04-09 | Component | Look for a cheaper alternative to CSD88539ND. Don't need such a high-performance FET | Cheaper | No | Sticking with this fet, SO-8 is very common, can be substituted for cheaper fet
2016-04-09 | Schematics | Use a smaller cap (2.2uF) for surface mount | Reduce space. Current caps are too big | Yes | Done
2016-04-09 | Layout | Place both arduinos on the same side | Only 1 arduino should be installed at a time. This will remove ambiguity | TBD, depends on how hard it is to re-layout | Requires complete re-layout, so not going to do it this version, maybe in future versions
2016-04-09 | Layout | Move pins on RTC closer to edge. Or on board if above change is implemented | RTC fits too snug against side of Xiaomi box | Depends on item 6 | Implemented
2016-04-09 | Schematics | Add a 10k resistor, parallel to C1 | Contrast pin does not sink enough current to reduce the output voltage of the PWM, so contrast pin always goes high regardless of PWM | Yes | Implemented
2016-04-09 | Schematics | U5 and U4 are using NFET, when it's wired as a PFET. Use a PFET | The body diode of the CSD88539 will become forward biased when LEDs are connected, causing the LEDs to turn on (regardless of gate voltage), and the chip gets very hot | Yes, changed NFET wiring | Done
2016-04-09 | Silkscreen | Label pin 1 on LED header J7 | Removes guess work of checking the back of the board to see which pin is 1 | Yes | Top left is pin 1, easily recognizable. No action
2016-04-09 | Layout | Rotary encoder through-hole pins should increase in size | Cannot slide pins into through-hole for rotary encoder | Yes | Done
2016-04-09 | Other | Find a better box to put electronics in. | I have a very limited stock of xiaomi band boxes | TBD | Critical
2016-04-16 | Schematics | Add thermal pads under FETs | Fets get very hot, used for thermal releif | No | Not required, as it would still operate within specs, though, better ventilation might help