## Sheet1
Date | Type | Mistake/note | Effect | Corrected in Rev2? | Comment
2016-04-09 | Footprint | CSD88539ND is a NFET. Currently connected as PFET | Body diode will cause the transistor to be always ON | Yes, changed NFET wiring
2016-04-09 | Silkscreen | YQ on silkscreen is backwards for both front and back | Visual | Yes
2016-04-09 | Component | Look for a cheaper alternative to CSD88539ND. Don't need such a high-performance FET | Cheaper | TBD
2016-04-09 | Schematics | Use a smaller cap (2.2uF) for surface mount | Reduce space. Current caps are too big | Yes
2016-04-09 | Layout | Place both arduinos on the same side | Only 1 arduino should be installed at a time. This will remove ambiguity | TBD, depends on how hard it is to re-layout
2016-04-09 | Layout | Move pins on RTC closer to edge. Or on board if above change is implemented | RTC fits too snug against side of Xiaomi box | Depends on item 6
2016-04-09 | Schematics | Add a 10k resistor, parallel to C1 | Contrast pin does not sink enough current to reduce the output voltage of the PWM, so contrast pin always goes high regardless of PWM | Yes
2016-04-09 | Schematics | U5 and U4 are using NFET, when it's wired as a PFET. Use a PFET | The body diode of the CSD88539 will become forward biased when LEDs are connected, causing the LEDs to turn on (regardless of gate voltage), and the chip gets very hot | Yes
2016-04-09 | Silkscreen | Label pin 1 on LED header J7 | Removes guess work of checking the back of the board to see which pin is 1 | Yes
2016-04-09 | Layout | Rotary encoder through-hole pins should increase in size | Cannot slide pins into through-hole for rotary encoder | Yes
2016-04-09 | Other | Find a better box to put electronics in. | I have a very limited stock of xiaomi band boxes | TBD | Critical